## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-360
JTRS GMR
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 3
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 8
Track To Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 19
Nuclear Cost |  | 19
Foreign Military Sales |  | 19
Unit Cost |  | 20
Cost Variance |  | 23
Contracts |  | 26
Deliveries and Expenditures |  | 27
Operating and Support Cost |  | 28

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
Joint Tactical Radio System Ground Mobile Radio (formerly Cluster 1) (JTRS GMR)
DoD Component
DoD
Joint Participants
US Army; US Navy; US Air Force; US Marine Corps; Army is the lead Component per SECDEF Memo dated August 31, 2009
Responsible Office
Responsible Office
COL Gregory Fields 33050 Nixie Way Bldg. 17B, Suite 121 San Diego, CA 92147
Phone Fax
DSN Phone DSN Fax
619-524-5765
619-524-5770
--
--
gregory.m.fields@us.army.mil Date Assigned August 28, 2009
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 24, 2002
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 16, 2008
Mission and Description
The Joint Tactical Radio Systems (JTRS) Ground Mobile Radios (GMR) will enable the Services to acquire and field a family of affordable, scalable, high capacity, interoperable radio sets based on a common set of JTRS Application Programming Interfaces (APIs) developed in accordance with the JTRS Software Communications Architecture (SCA). The JTRS is a key enabler of the DOD and Army Transformation and will provide critical communications capabilities across the full spectrum of operations in a Joint environment. It is a Joint program encompassing the incorporation of the JTRS Network Enterprise Domain (NED) developed waveforms (porting) and Ground Vehicular applications.

## Table 4
Executive Summary
On October 13, 2011, the Under Secretary of Defense for Acquisition, Technology and Logistics (USD
(AT&L)) notified Congress that the Joint Tactical Radio Systems Ground Mobile Radios (JTRS GMR) program is canceled; therefore, this is the final SAR submission for JTRS GMR.
In May 2011, the USD (AT&L) initiated a comprehensive reassessment of the GMR program due to a Nunn-McCurdy breach. A quarterly exception SAR was submitted in June 2011 to report the Nunn-McCurdy breach. The immediate cause of the breach was the reduction in quantity from 86,209 to 10,293, due to a revised Basis of Issue based on a new Operational Network Architecture and the cancellation of the Future Combat System. The Nunn-McCurdy breach was reported to Congress in the June 2011 SAR.
On October 14, 2011, a Nunn-McCurdy review Acquisition Decision Memorandum (ADM) was released that detailed the outcome of the reassessment of the GMR program. Conclusions of the reassessment did not support certification of the program, thereby cancelling it.
The ADM directed the program to continue with completion and closeout activities of the existing GMR System Development and Demonstration (SDD) contract. The Program Management Office (PMO) is to identify critical deliverables such as hardware, design specifications, instrumentation, modeling tools, simulators, etc. for delivery to the Government in order to assure their delivery and acceptance prior to contract expiration in March 2012.
The ADM also included direction to complete National Security Administration (NSA) certification of the current radio, operating environment, and Wideband Networking Waveform (WNW). These products are essential to facilitate future acquisitions in support of operational requirements.
There are no significant software-related issues with this program at this time.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Current UCR Baseline
PAUC Critical
APUC None
Original UCR Baseline
PAUC Critical
APUC None
Explanation of Breach
Schedule: The schedule breach was previously reported in the June 2011 SAR.
Cost: The RDT&E cost breach was previously reported in the June 2011 SAR.
Unit Cost: A critical PAUC Nunn-McCurdy unit cost breach was previously reported in the June 2011 SAR against the current and original baselines. A significant APUC Nunn-McCurdy unit cost breach was previously reported in the June 2011 SAR against the current and original baselines.
The necessary review processes to address the Nunn-McCurdy certification criteria were implemented. Based on findings and facts of the Integrated Product Teams (IPTs), the Milestone Decision Authority
(MDA) issued an Acquisition Decision Memorandum (ADM) on October 14, 2011 to not certify the continuation of the JTRS GMR Program. The ADM also included direction to complete National Security Administration (NSA) certification of the current radio, operating environment, and Wideband Networking Waveform (WNW). These products are essential to facilitate future acquisitions in support of operational requirements.
On October 13, 2011, the Under Secretary of Defense for Acquisition, Technology and Logistics (USD(AT&L)) notified Congress that the GMR program is canceled.
Nunn-McCurdy Breaches

## Table 6
Schedule

## Table 7
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B Decision | JUN 2002 | JUN 2002 | DEC 2002 | JUN 2002
Contract Award | JUN 2002 | JUN 2002 | DEC 2002 | JUN 2002
Early Operational Assessment
Start | APR 2004 | N/A | N/A | N/A
Complete | JUN 2004 | N/A | N/A | N/A
Long Lead Item Procurement Option 1 Approval OIPT | SEP 2004 | N/A | N/A | N/A
Delivery of Airborne B Kits to Aviation for Airworthiness Certification and Integration | AUG 2004 | N/A | N/A | N/A
Development Test/Operational Test/Limited User Test
Start | FEB 2005 | N/A | N/A | N/A
Complete | JUL 2005 | N/A | N/A | N/A
Milestone C Decision | AUG 2005 | JUL 2010 | JUL 2011 | N/A 1
LRIP Option 1 Exercise | SEP 2005 | N/A | N/A | N/A
First Article Test
Start | JAN 2006 | N/A | N/A | N/A
Complete | APR 2006 | N/A | N/A | N/A
MOT&E
Start | AUG 2006 | OCT 2011 | OCT 2012 | N/A 1
Complete | OCT 2006 | DEC 2011 | DEC 2012 | N/A 1
First Unit Equipped (FUE) | JAN 2007 | N/A | N/A | N/A
Initial Operational Capability | N/A | DEC 2011 | JUN 2013 | N/A 1
Full Rate Production In Process Review | FEB 2007 | DEC 2011 | DEC 2012 | N/A 1
Full Rate Production Contract Award | JAN 2007 | N/A | N/A | N/A
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
1APB Breach
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Acronyms And Abbreviations
LRIP - Low Rate Initial Production
MOT&E - Multi-Service Operational Test and Evaluation OIPT - Overarching Integrated Product Team
Change Explanations
(Ch-1) The Defense Acquisition Executive (DAE) signed an Acquisition Decision Memorandum (ADM) on October 14, 2011 which directed cancellation of the JTRS GMR Program. Consequently, there are no upcoming schedule milestones.

## Table 8
Performance
Characteristics | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Have an internal | Open | Open | Open | TBD | Open
growth capability | System | system | system |  | system
| Architecture | architecture | architecture |  | architecture
| IAW JTA; | in | in |  | in
| Modular, | accordance | accordance |  | accordance
| Scaleable, | with DISR; | with DISR; |  | with DISR;
| Flexible | Modular, | Modular, |  | Modular,
| Form Factors | Scaleable, | Scaleable, |  | Scaleable,
|  | Flexible | Flexible |  | Flexible
|  | Form Factors | Form Factors |  | Form
Factors.
JTR set | By operators | By operators | By operators | TBD | By operators
modes/capabilities | in their | in their | in their |  | in their
configuration and | operational | operational | operational |  | operational
reconfiguration via | environment | environment | environment |  | environment.
software
Multi-channel routing | Objective | Objective | KPP | TBD | KPP
and retransmission | waveforms | waveforms | waveforms |  | waveforms
| that are | that are | that are |  | that are
| compatible | same in | same in |  | same in
| in mode | mode (voice, | mode (voice, |  | mode (voice,
| (voice, data, | data, or | data, or |  | data, or
| or video) | video) and | video) and |  | video) and
| and use | use like data | use like data |  | use like data
| compatible | rates and | rates and |  | rates and
| data rates | operate at | operate at |  | operate at
|  | permissible | permissible |  | permissible
|  | security | security |  | security
|  | classification | classification |  | classification
|  | levels | levels |  | levels.
Support time-critical | SINCGARS | See | See | TBD | See
waveforms | ESIP (MIL- | Annexes D | Annexes D |  | Annexes D
| STD188- | and F of | and F of |  | and F of
| 220) HAVE | ORD 3.2.1 | ORD 3.2.1 |  | ORD 3.2.1.
QUICK II
UHF DAMA
SATCOM
(MIL-STD
188-181)
w/EPLRS
WNW (new,
modified or
existing
waveform)
and non-
KPP LINK-

## Table 9
16 (-) for TACP
Operate on designated number of channels at the same time | GPS+8 (Vehicular), GPS+10 (Airborne) | 8 Vehicular | 4 Vehicular | TBD | GPS+4 (Vehicular)
Scaleable networking services | Maritime/Fix- ed Domain | All Domains | All Domains | TBD | All Domains
Network extension/coverage | Across Organization- al boundaries | Across organization- al boundaries | Across organization- al boundaries | TBD | Across organiza- tional boundaries.
JTR System network interoperability | Inter-operate with Allied/Coaliti on and commercial networks; satisfy 100% of top-level IERs | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements in the Joint integrated architecture | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements designated as enterprise- level or critical in the Joint integrated architecture | TBD | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements designated as enterprise level or critical in the Joint integrated architecture.
Operational Availability (Ao) | 0.99 Channel / 0.96 (Set) | 0.99 Channel/0.96 (Set) | 0.96 Channel | TBD | 0.96 (Channel)
Net Ready (NR) capability | N/A | The system must fully support executionof all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical | TBD | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical

## Table 10
requirements | requirements | requirements
for Net- | for transition | for transition
Centric | to Net- | to Net-
military | Centric | Centric
operations | military | military
to include: 1) | operations | operations
DISR | to include: 1) | to include: 1)
mandated | DISR | DISR
GIG IT | mandated | mandated
standards | GIG IT | GIG IT
and profiles | standards | standards
identified in | and profiles | and profiles
the TV1 2) | identified in | identified in
DISR | the TV1 2) | the TV1 2)
mandated | DISR | DISR
GIG KIPs | mandated | mandated
identified in | GIG KIPs | GIG KIPs
the KIP | identified in | identified in
declaration | the KIP | the KIP
(Table 31) 3) | declaration | declaration
NCOW RM | (Table 31) 3) | (Table 31) 3)
Enterprise | NCOW RM | NCOW RM
Services 4) | Enterprise | Enterprise
Information | Services 4) | Services 4)
assur-ance | IA | IA
requirements | requirements | requirements
including | including | including
availability, | availability, | availability,
integrity, | integrity, | integrity,
authenticat- | authenticat- | authenti-
ion, | ion, | cation,
confidential- | confidential- | confidentiality
ity, and | ity, and | , and non-
nonrepudiat- | nonrepudiat- | repudiation,
ion, and | ion, and | and
issuance of | issuance of | issuance of
an ATO by | an IATO by | an IATO by
the DAA 5) | the DAA 5) | the DAA 5)
Operationally | Operationally | Operationally
effective | effective | effective
information | information | information
exchanges; | exchanges; | exchanges;
and mission | and mission | and mission
critical | critical | critical
performance | performance | performance
and IA | and IA | and IA
attributes, | attributes, | attributes,
data | data | data
correctness, | correctness, | correctness,
data | data | data
availability, | availability, | availability,
and | and | and
consistent | consistent | consistent
data | data | data

## Table 11
| processing | processing | processing
| specified in | specified in | specified in
| the | the | the
| applicable | applicable | applicable
| joint and | joint and | joint and
| system | system | system
| integrated | integrated | integrated
| architecture | architecture | architecture
| views | views | views.
Requirements Source: Increment 1 JTRS Ground Mobile Radio (GMR) Performance Requirements for Increment 1 are based on JROCM 131-06 dated June 29, 2006 and JROCM 171-06 dated August 28, 2006. The JROCM 131-06 mandated the NR KPP and JROCM 171-06 approved the ORD version 3.2
Acronyms And Abbreviations
Ao - Operational Availability ATO - Authority To Operate
DAA - Designated Approving Authority DAMA - Demand Assigned Multiple Access
DISR - DoD Information Technology Standards Registry
DoD IEA - Department of Defense Information Enterprise Architecture DoDAF - Department of Defense Architecture Framework
EDM - Engineering Development Model
EPLRS - Enhanced Position Location Reporting System ESIP - Enhanced SINCGARS Improvement Program GIG - Global Information Grid
GPS - Global Positioning System IA - Information Assurance
IATO - Interim Authority To Operate IAW - In Accordance With
IER - Information Exchange Requirement IT - Information Technology
JROCM - Joint Requirements Oversight Council Memorandum JTA - Joint Technical Architecture
JTR - Joint Tactical Radio KIP - Key Interface Profile
KPP - Key Performance Parameters MIL-STD - Military Standard
NCOW-RM - Net Centric Operations and Warfare - Reference Model NR - Net Ready
ORD - Operational Requirements Document
SAASM - Selective Availability Anti-Spoofing Module SATCOM - Satellite Communications
SINCGARS - Single Channel Ground and Airborne Radio System TACP - Tactical Air Control Party
TBD - To Be Determined TV - Technical View
UHF - Ultra High Frequency
WNW - Wideband Networking Waveform
Change Explanations
None

## Table 12
Memo
On April 29, 2011, the Vice Chairman of the Joint Chiefs of Staff issued two memos, the first stating that the Joint Requirements Oversight Council (JROC) approved GMRs requested modification of the waveform Key Performance Parameter (KPP) in the Operational Requirements Document (ORD) 3.2.1 (Amendment). The first memo changed the EPLRS waveform from a Threshold to an Objective requirement across the JTRS Enterprise. The second memorandum approved changing the Multi-channel routing and retransmission of non-Internet Protocol data to Internet Protocol data from a Threshold to an Objective requirement across the JTRS Enterprise.

## Table 13
Track To Budget
RDT&E
APPN 1319 | BA 05 | PE 0604280N | (Navy)
| Project 3074 | Joint Tactical Radio System (JTRS) / GMR JTRS | (Shared)
| Project 9999 | Army Tactical Radios for FCS | (Shared) | (Sunk)
APPN 2040 | BA 05 | PE 0604280A | (Army)
| Project 162 | Joint Tactical Radio / Network Enterprise Domain (NED) | (Shared)
APPN 2040 | BA 05 | PE 0604805A | (Army)
| Project D615 | Command, Project 615 Control, Comm Systems - Eng Dev/JTRS- Ground Domain Integration | (Shared) | (Sunk)
The JTRS Common RDT&E funding is consolidated under one Navy Program Element (PE 0604280N) in the execution and budget years (FY 2010 - FY 2012). Army Program Element (PE 0604805A) represents prior year funding.
Procurement
APPN 1109 BA 04 PE 0206313M (Navy)
ICN 4633 Marine Corps Communication Equipment / Radio Systems
(Shared)
APPN 2035 BA 02 PE 0310700A (Army)
ICN B90100 JTRS Cluster 1 (GMR) (Shared)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2002 $M |  |  |  | BY2002 $M |  | TY $M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 845.1 | 1209.8 |  | 1330.9 | 1454.5 1 |  | 901.1 | 1356.7 | 1652.4
Procurement | 13592.1 | 13060.9 |  | 14367.1 | 0 |  | 18211.8 | 19387.1 | 0
Flyaway | 11855.4 | -- |  | -- | 0 |  | 15879.3 | -- | 0
Recurring | 11855.4 | -- |  | -- | 0 |  | 15879.3 | -- | 0
Non Recurring | 0 | -- |  | -- | 0 |  | 0 | -- | 0
Support | 1736.7 | -- |  | -- | 0 |  | 2332.5 | -- | 0
Other Support | 1087.3 | -- |  | -- | 0 |  | 1462.7 | -- | 0
Initial Spares | 649.4 | -- |  | -- | 0 |  | 869.8 | -- | 0
MILCON | 0 | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 14437.2 | 14270.7 |  | N/A | 1454.5 |  | 19112.9 | 20743.8 | 1652.4
1 APB Breach
Quantity | SAR Baseline Dev Est |  | Current APB Development |  |  | Current Estimate
RDT&E | 302 |  | 140 |  |  | 91
Procurement | 108086 |  | 86512 |  |  | 0
Total | 108388 |  | 86652 |  |  | 91
The unit of measure is a JTRS GMR radio set which is capable of running 2, 3, or 4 channels.
Because of the non-certification of the JTRS GMR Program by the Defense Acquisition Executive (DAE) on October 14, 2011, the quantity is now zero.

## Table 15
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
Appropriation | Prior | FY2012 |  | FY2013 |  | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | T | otal
RDT&E | 1582.7 | 69.7 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1652.4
Procurement | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 1582.7 | 69.7 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1652.4
PB 2012 Total | 1730.7 | 231.4 |  |  | 276.1 | 262 | 209.7 |  | 251.7 |  | 251.1 |  | 16289.1 |  | 19501.8
Delta | -148 | -161.7 |  |  | -276.1 | -262 | -209.7 |  | -251.7 |  | -251.1 |  | -16289.1 |  | -17849.4
Quantity | ndistributed |  | Prior |  | FY2012 | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 91 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 91
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
PB 2013 Total | 91 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 91
PB 2012 Total | 91 |  | 308 |  | 490 | 629 | 608 |  | 522 |  | 689 712 |  |  | 82907 |  | 86956
U
Delta 0 -308 -490 -629 -608 -522 -689 -712 -82907 -
86865

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | -- | -- | -- | -- | -- | 202.9
2008 | -- | -- | -- | -- | -- | -- | 262.8
2009 | -- | -- | -- | -- | -- | -- | 245.8
2010 | -- | -- | -- | -- | -- | -- | 200.4
2011 | -- | -- | -- | -- | -- | -- | 99.3
2012 | -- | -- | -- | -- | -- | -- | 69.7
Subtotal | 91 | -- | -- | -- | -- | -- | 1080.9

## Table 17
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2007 | -- | -- | -- | -- | -- | -- | 178
2008 | -- | -- | -- | -- | -- | -- | 226.5
2009 | -- | -- | -- | -- | -- | -- | 209.1
2010 | -- | -- | -- | -- | -- | -- | 168
2011 | -- | -- | -- | -- | -- | -- | 81.7
2012 | -- | -- | -- | -- | -- | -- | 56.3
Subtotal | 91 | -- | -- | -- | -- | -- | 919.6

## Table 18
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2002 | -- | -- | -- | -- | -- | -- | 49.6
2003 | -- | -- | -- | -- | -- | -- | 87.8
2004 | -- | -- | -- | -- | -- | -- | 169.8
2005 | -- | -- | -- | -- | -- | -- | 97.2
2006 | -- | -- | -- | -- | -- | -- | 167.1
Subtotal | -- | -- | -- | -- | -- | -- | 571.5

## Table 19
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2002 | -- | -- | -- | -- | -- | -- | 49.1
2003 | -- | -- | -- | -- | -- | -- | 85.3
2004 | -- | -- | -- | -- | -- | -- | 161
2005 | -- | -- | -- | -- | -- | -- | 89.6
2006 | -- | -- | -- | -- | -- | -- | 149.9
Subtotal | -- | -- | -- | -- | -- | -- | 534.9
Low Rate Initial Production
At the Milestone B, Low Rate Initial Production (LRIP) was not to exceed ten percent (10%) of total Production for all Services. Due to program cancellation, JTRS GMR will not enter into production.
Foreign Military Sales
None
Nuclear Cost
None

## Table 20
Unit Cost
Unit Cost Report
|  | BY2002 $M | BY2002 $M
Unit Cost |  | Current UCR Baseline (JAN 2008 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 14270.7 |  |  | 1454.5
Quantity | 86652 |  |  | 91
Unit Cost | 0.165 |  |  | 15.984 |  | +9587.27 1
Average Procurement Unit Cost (APUC)
Cost | 13060.9 |  |  | 0
Quantity | 86512 |  |  | 0
Unit Cost | 0.151 |  |  | -- |  | --
|  | BY2002 $M | BY2002 $M
Unit Cost |  | Original UCR Baseline (JUN 2002 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 14437.2 |  |  | 1454.5
Quantity | 108388 |  |  | 91
Unit Cost | 0.133 |  |  | 15.984 | +11918.05 1
Average Procurement Unit Cost (APUC)
Cost | 13592.1 |  |  | 0
Quantity | 108086 |  |  | 0
Unit Cost | 0.126 |  |  | -- | --
1 Nunn-McCurdy Breach
The JTRS GMR Program Office reported a Nunn-McCurdy breach on June 24, 2011. Congress was notified of the critical Nunn-McCurdy breach on May 13, 2011. The JTRS GMR Program Office reported the Nunn-McCurdy breach in the June 2011 SAR.
In the June 2011 SAR the reported PAUC deviation against the current and original baseline was 92.12% and 138.35%, respectively. In the June 2011 SAR the reported APUC deviation against the current and original baseline was 23.18% and 47.62%, respectively. Following the required Nunn-McCurdy certification process, the Defense Acquisition Executive (DAE) decided not to certify the continuation of the existing JTRS GMR Program. An Acquisition Decision Memorandum (ADM) was signed by the DAE on October 14, 2011 authorizing cancellation.
As a result of the program cancellation, the total procurement quantity has been reduced from 10,293 to 0. This has resulted in a calculated increase to the PAUC from the June 2011 SAR.

## Table 21
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[8 empty] | BY2002 $M | [5 empty] | TY $M
|  |  |  | Date |  |  |  | PAUC |  |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  |  | JUN 2002 |  |  |  | 0.133 |  |  | 0.126 |  |  | 0.176 |  | 0.168
APB as of January 2006 |  |  |  | JUN 2002 |  |  |  | 0.133 |  |  | 0.126 |  |  | 0.176 |  | 0.168
Revised Original APB |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  |  | JUN 2002 |  |  |  | 0.133 |  |  | 0.126 |  |  | 0.176 |  | 0.168
Current APB |  |  |  | JAN 2008 |  |  |  | 0.165 |  |  | 0.151 |  |  | 0.239 |  | 0.224
Prior Annual SAR |  |  |  | DEC 2010 |  |  |  | 0.156 |  |  | 0.14 |  |  | 0.224 |  | 0.205
Current Estimate |  |  |  | DEC 2011 |  |  |  | 15.984 |  |  | N/A |  |  | 18.158 |  | N/A
Initial PAUC Dev Est | Changes | [13 empty] | PAUC Current Est
| Econ | Qty |  |  | Sch | Eng | Est |  | Oth |  | Spt |  | Total
0.176 0.046 24.109 13.077 -0.757 7.042 0.000 -25.535 17.982 18.158
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [13 empty] | APUC Current Est
| Econ |  | Qty |  | Sch | Eng | Est |  |  | Oth |  | Spt | Total
0.168 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 22
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | JUN 2002 | N/A | JUN 2002
Milestone C | N/A | AUG 2005 | N/A | N/A
IOC | N/A | N/A | N/A | N/A
Total Cost (TY $M) | N/A | 19112.9 | N/A | 1652.4
Total Quantity | N/A | 108388 | N/A | 91
Prog. Acq. Unit Cost (PAUC) | N/A | 0.176 | N/A | 18.158

## Table 23
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 901.1 | 18211.8 | -- | 19112.9
Previous Changes
Economic | 20.9 | -67.9 | -- | -47
Quantity | 9.3 | -14718.7 | -- | -14709.4
Schedule | 392.2 | 802.5 | -- | 1194.7
Engineering | -126.6 | 58.2 | -- | -68.4
Estimating | 469.9 | -69.7 | -- | 400.2
Other | -- | -- | -- | --
Support | -- | -1508.9 | -- | -1508.9
Subtotal | 765.7 | -15504.5 | -- | -14738.8
Current Changes
Economic | 3.5 | 47.7 | -- | 51.2
Quantity | -- | -2193.5 | -- | -2193.5
Schedule | -- | -4.7 | -- | -4.7
Engineering | -- | -0.5 | -- | -0.5
Estimating | -17.9 | 258.5 | -- | 240.6
Other | -- | -- | -- | --
Support | -- | -814.8 | -- | -814.8
Subtotal | -14.4 | -2707.3 | -- | -2721.7
Total Changes | 751.3 | -18211.8 | -- | -17460.5
CE - Cost Variance | 1652.4 | -- | -- | 1652.4
CE - Cost & Funding | 1652.4 | -- | -- | 1652.4

## Table 24
Summary Base Year 2002 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Dev Est) Previous Changes |  | 845.1 | 13592.1 | -- | 14437.2
Economic |  | -- | -- | -- | --
Quantity |  | 8.8 | -9667 | -- | -9658.2
Schedule |  | 346.4 | -761.9 | -- | -415.5
Engineering |  | -105.2 | -21.5 | -- | -126.7
Estimating |  | 372.1 | 28.2 | -- | 400.3
Other |  | -- | -- | -- | --
Support |  | -- | -1139.3 | -- | -1139.3
Subtotal |  | 622.1 | -11561.5 | -- | -10939.4
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -1616.3 | -- | -1616.3
Schedule |  | -- | -2.6 | -- | -2.6
Engineering |  | -- | -0.2 | -- | -0.2
Estimating |  | -12.7 | 185.9 | -- | 173.2
Other |  | -- | -- | -- | --
Support |  | -- | -597.4 | -- | -597.4
Subtotal |  | -12.7 | -2030.6 | -- | -2043.3
Total Changes |  | 609.4 | -13592.1 | -- | -12982.7
CE - Cost Variance |  | 1454.5 | -- | -- | 1454.5
CE - Cost & Funding |  | 1454.5 | -- | -- | 1454.5
Previous Estimate: June 2011

## Table 25
RDT&E |  |  |  | $M
Current Change Explanations |  |  |  | Base Year |  | Then Year
Revised escalation indices. (Economic) |  |  |  | N/A |  | 3.5
Navy: Estimating increase associated with the completion of testing activities on the JTRS GMR Engineering, Manufacturing and Development (EMD) contract. |  |  |  | 41.2 |  | 51
(Estimating)
Navy: Estimating decrease associated with the formal cancellation of the JTRS GMR Program. No requirements exist beyond FY 2012. (Estimating)
Army: Estimating increase associated with the completion of testing activities on the JTRS GMR Engineering, Manufacturing and Development (EMD) contract. (Estimating)
Air Force: Estimating decrease associated with the cancellation of the JTRS GMR Program. No requirements are forecasted beyond FY 2012. (Estimating)
-4.0 -5.1
-44.9 -57.7
-2.9 -3.6
Adjustment for current and prior escalation. (Estimating) |  | -2.1 |  |  |  |  | -2.5
RDT&E Subtotal |  | -12.7 |  |  |  |  | -14.4
Procurement |  |  |  | $M
Current Change Explanations |  |  |  | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A +47.7
Quantity variance resulting from a decrease of 10293 JTRS GMRs from 10293 to 0 (Army). (Quantity)
Total Quantity variance resulting from a decrease of 646 JTRS GMRs from 646 to 0 (Navy). (Subtotal)
Quantity variance resulting from a decrease of 646 JTRS GMRs from 646 to 0 (Navy). (Quantity)
-1523.6 | -2060.1
-95.3 | -138.1
-92.7 | -133.4
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) |  |  | -2.6 |  | -4.7
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) |  |  | -0.2 |  | -0.5
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) |  |  | -0.2 |  | -0.5
Additional cost variance associated with the cancellation of Program (Army). (Estimating) (QR)
Additional cost variance associated with the cancellation of Program (Navy). (Estimating) (QR)
+230.5 +321.5
-42.2 -60.3
Adjustment for current and prior escalation. (Estimating) |  | -2.6 |  |  |  |  | -3.2
Adjustment for current and prior escalation. (Support) |  | -0.8 |  |  |  |  | -1
Decrease in Other Support to reflect cancellation of the JTRS GMR program (Army). (Support) (QR)
Decrease in Initial Spares to reflect cancellation of the JTRS GMR program (Army). (Support) (QR)
Decrease in Other Support to reflect cancellation of the JTRS GMR program (Navy). (Support) (QR)
Decrease in Initial Spares to reflect cancellation of the JTRS GMR program (Navy). (Support) (QR)
-479.8 -654.3
-89.5 -120.0
-17.6 -25.5
-9.7 -14.0
Procurement Subtotal -2030.6 -2707.3
(QR) Quantity Related

## Table 26
Contracts
There are no Contracts data to display.

## Table 27
Deliveries and Expenditures
The Expenditures to Date is as of December 31, 2011.
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 91 |  | 91 |  | 91 | 100%
Production | 0 |  | 0 |  | 0 | --
Total Program Quantities Delivered | 91 |  | 91 |  | 91 | 100%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 1652.4 | Years Appropriated |  |  | 11
Expenditures To Date | 1573.6 | Percent Years Appropriated |  |  | 100%
Percent Expended | 95.23% | Appropriated to Date |  |  | 1652.4
Total Funding Years | 11 | Percent Appropriated |  |  | 100%

## Table 28
Operating and Support Cost
Assumptions And Ground Rules
There are no calculated Operations and Support (O&S) costs against the JTRS GMR Program as a result of the program cancellation.
Costs BY2002 $K
Cost Element | JTRS GMR Average Annual Cost (Per Radio) | No Antecedent
Unit-Level Manpower | -- | --
Unit Operations | 0 | --
Maintenance | -- | --
Sustaining Support | 0 | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | -- | --
Total O&S Costs $M | JTRS GMR | No Antecedent
Base Year | 0 | --
Then Year | 0 | --