## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-357
LAIRCM
As of September 30, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 7
Track To Budget |  | 8
Cost and Funding |  | 9
Low Rate Initial Production |  | 12
Foreign Military Sales |  | 12
Nuclear Cost |  | 13
Unit Cost |  | 14
Cost Variance |  | 17
Contracts |  | 20
Deliveries and Expenditures |  | 21
Operating and Support Cost |  | 22

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
Large Aircraft Infrared Countermeasures
DoD Component
Air Force
Responsible Office
Responsible Office
Col. Shawn Shanley | Phone | 937-656-6285
2275 D. Street | Fax | 937-255-9963
Bldg 16 | DSN Phone | 986-6285
Room 067 Wright-Patterson Air Force Base, OH 45433 | DSN Fax | 785-9955
Shawn.Shanley@WPAFB.AF.MIL | Date Assigned | June 30, 2011
References
SAR Baseline (Production Estimate)
FY 2009 President's Budget dated February 2008
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated August 24, 2009

## Table 4
Mission and Description
Large Aircraft Infrared Countermeasures (LAIRCM) provides defense for large aircraft from widespread and growing threat of man-portable air defense systems (MANPADs), shoulder fired and mobile launched infrared (IR) surface-to- air missiles. The LAIRCM system autonomously detects, declares, tracks, and jams infrared (IR) threat missiles to create a miss, resulting in aircrew and aircraft protection. The system has no interoperability requirements outside the platform on which it is installed. The LAIRCM system consists primarily of four subsystem components: a System Processor (SP), a Control Indicator Unit (CIU), an AAR-54 Missile Warning System (MWS) and a laser transmitter assembly. Initially the program used the Small Laser Transmitter Assembly (SLTA); however, most new installations incorporate the improved transmitter assembly termed the Guardian Laser Transmitter Assembly (GLTA). The GLTA has the following advantages over the SLTA: reduced turret procurement cost; significant reliability improvement; increased energy on target; and weight and drag reductions.
Major Defense Acquisition Program (MDAP) funding ends in FY 2012 for the Research, Development, Test and Evaluation effort of the LAIRCM program. Production funding is provided by the platforms and is not included in this Selected Acquisition Report. Systems upgrades to maintain currency with threats, increase operational capability, and increase Reliability, Availability and Maintainability will continue beyond FY 2012.
Executive Summary
This quarterly exception SAR is being submitted to terminate reporting for the LAIRCM program. As of September 2011, the LAIRCM program is greater than 90 percent expended, therefore; pursuant to section 2432 of title 10, United State Code, this is the final SAR.
The LAIRCM system is installed on 279 Mobility Air Force (MAF) and Air Force Special Operations Command (AFSOC) aircraft.
Final development efforts are planned for the LAIRCM integration on AFSOC EC-130J and AC-130U aircraft. The aircraft are the last two in the development effort due to their high demand in theater and non-availability for integration efforts.
LAIRCM production cost will be managed under Air Force oversight as Acquisition Category II and III programs for the C-130, C-130J, C-17, C-5, and HC/MC-130J aircraft.
There are no significant software issues with the program at this time.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 6
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
LAIRCM Basic
Milestone B | SEP 2001 | SEP 2001 | SEP 2001 | SEP 2001
DT&E Complete | JAN 2002 | JAN 2002 | JAN 2002 | JAN 2002
Milestone C | AUG 2002 | AUG 2002 | AUG 2002 | AUG 2002
IOT&E Complete | MAR 2004 | MAR 2004 | MAR 2004 | MAR 2004
RAA Complete | JUL 2004 | JUL 2004 | JUL 2004 | JUL 2004
NexGen
NexGen Milestone B | N/A | JUN 2004 | JUN 2004 | JUN 2004
NexGen DT&E Complete | N/A | AUG 2006 | AUG 2006 | AUG 2006
NexGen Milestone C | N/A | MAY 2008 | MAY 2008 | MAY 2008
NexGen DT/OT Complete | N/A | SEP 2010 | MAR 2011 | DEC 2010
Acronyms And Abbreviations
DT&E - Developmental Test and Evaluation DT/OT - Developmental Test/Operational Test IOT&E - Initial Operational Test and Evaluation NexGen - Next Generation missile warning system RAA - Required Assets Available
Change Explanations
None

## Table 7
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Operability | N/A | System shall | System shall | Meets | System shall
|  | not interfere | not interfere | requirements | not interfere
|  | with flight | with flight |  | with flight
|  | character- | character- |  | character-
|  | istics or | istics or |  | istics or
|  | mission | mission |  | mission
|  | requirements | requirements |  | requirements
Requirements Source:
- USAF and AMC Mission Need Statements for Advanced Infrared Countermeasures (IRCM) 014-92, March 26, 1993
- USAF Multi-Command (Air Mobility Command (AMC), Air Combat Command (ACC), Air Force Special Operations - Command [AFSOC]) Operational Requirements Document (ORD) 314-92, August 3, 1998
- AMC LAIRCM Phase I ORD Annex validated by the Air Force Requirements Oversight Council (AFROC) on January 25, 2001
- AMC Combat Mission Needs Statement (CMNS) IRCM capability November 2, 2002
Change Explanations
None
Classified Performance information is provided in the classified annex to this submission.

## Table 8
Track To Budget
RDT&E
APPN 3600 | BA 07 Project 674942 | PE 0401134F LAIRCM | (Air Force) (Shared)
LAIRCM funding for the Major Defense Acquisition Program ends in FY 2012. The funding past FY 2012 is excluded from this report. It represents upgrades to maintain the LAIRCM capability current with future threats.

## Table 9
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2008 $M |  |  |  |  | BY2008 $M |  | TY $M
Appropriation | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 383.6 |  | 457 |  | 500.6 | 436.6 |  | 366 | 438.6 | 413.1
Procurement | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Flyaway | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Non Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Other Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Initial Spares | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 383.6 |  | 457 |  | N/A | 436.6 |  | 366 | 438.6 | 413.1
The LAIRCM program is a Research, Development, Test and Evaluation effort only. Production funding is provided by the platforms and is not included in this Selected Acquisition Report.
The LAIRCM Acquisition Program Baseline (APB) is based on the Independent Cost Estimate (ICE) completed by the Air Force Cost Analysis Agency (AFCAA) in 2009. Due to the maturity of the program, AFCAA recommended the mean 55% confidence level.
Quantity |  | SAR Baseline Prod Est |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 8 |  | 8 |  |  | 8
Procurement |  | 0 |  | 0 |  |  | 0
Total |  | 8 |  | 8 |  |  | 8
The unit of measure is one aircraft modified with the LAIRCM system. The eight (8) development deliveries consist of (2) C-17s, (1) C-130H, (1) C-5, (1) C-130J, (1) AC-130H, (2) additional Air Force Special Operations Command (AFSOC) C-130 variants.

## Table 10
Cost and Funding
Funding Summary
Appropriation and Quantity Summary
SEP 2011 Exception SAR (TY $M)
Appropriation |  | Prior | FY2011 |  | FY2012 |  | FY2013 | FY2014 |  | FY2015 |  | FY2 | 16 | To Complete |  | T | otal
RDT&E |  | 388.5 | 17.1 |  | 7.5 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 413.1
Procurement |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
SEP 2011 Total |  | 388.5 | 17.1 |  | 7.5 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 413.1
PB 2012 Total |  | 388.5 | 17.2 |  | 7.5 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 413.2
Delta |  | 0 | -0.1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -0.1
Quantity |  | ndistributed |  | Prior |  | FY2011 | FY2012 | FY2013 | FY2014 |  | FY2015 |  | FY2016 |  | To Complete |  | Total
Development |  | 8 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
Production |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
SEP 2011 Total |  | 8 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
PB 2012 Total |  | 8 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
Delta |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
FY2012 President's Budget / December 2010 SAR (TY$ M)
Appropriation |  | Prior | FY2011 |  | FY2012 |  | FY2013 | FY2014 |  | FY2015 |  | FY2 | 16 | To Complete |  | T | otal
RDT&E |  | 388.5 | 17.2 |  | 7.5 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 413.2
Procurement |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2012 Total |  | 388.5 | 17.2 |  | 7.5 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 413.2
PB 2011 Total |  | 390.7 | 17.2 |  | 7.5 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 415.4
Delta |  | -2.2 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -2.2
U
The LAIRCM program is a Research, Development, Test and Evaluation effort only. Production funding is provided by the platforms and is not included in this Selected Acquisition Report.
Quantity | Undistributed |  |  | Prior |  | FY2011 | FY2012 | FY2013 | FY2014 |  | FY2015 |  | FY2016 |  | To Complete |  | Total
Development | 8 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 8
Production | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2012 Total | 8 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 8
PB 2011 Total | 8 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 8
Delta | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 11
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2002 | -- | -- | -- | -- | -- | -- | 51.5
2003 | -- | -- | -- | -- | -- | -- | 42.5
2004 | -- | -- | -- | -- | -- | -- | 48.4
2005 | -- | -- | -- | -- | -- | -- | 85.7
2006 | -- | -- | -- | -- | -- | -- | 61.3
2007 | -- | -- | -- | -- | -- | -- | 37.2
2008 | -- | -- | -- | -- | -- | -- | 14.8
2009 | -- | -- | -- | -- | -- | -- | 21.4
2010 | -- | -- | -- | -- | -- | -- | 25.7
2011 | -- | -- | -- | -- | -- | -- | 17.1
2012 | -- | -- | -- | -- | -- | -- | 7.5
Subtotal | 8 | -- | -- | -- | -- | -- | 413.1

## Table 12
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M |  | Non End Item Recurring Flyaway BY 2008 $M |  | Non Recurring Flyaway BY 2008 $M |  | Total Flyaway BY 2008 $M |  | Total Support BY 2008 $M | Total Program BY 2008 $M
2002 | -- | -- |  | -- |  | -- |  | -- |  | -- | 58.7
2003 | -- | -- |  | -- |  | -- |  | -- |  | -- | 47.8
2004 | -- | -- |  | -- |  | -- |  | -- |  | -- | 53.1
2005 | -- | -- |  | -- |  | -- |  | -- |  | -- | 91.7
2006 | -- | -- |  | -- |  | -- |  | -- |  | -- | 63.6
2007 | -- | -- |  | -- |  | -- |  | -- |  | -- | 37.6
2008 | -- | -- |  | -- |  | -- |  | -- |  | -- | 14.7
2009 | -- | -- |  | -- |  | -- |  | -- |  | -- | 21
2010 | -- | -- |  | -- |  | -- |  | -- |  | -- | 24.9
2011 | -- | -- |  | -- |  | -- |  | -- |  | -- | 16.4
2012 | -- | -- |  | -- |  | -- |  | -- |  | -- | 7.1
Subtotal | 8 | -- |  | -- |  | -- |  | -- |  | -- | 436.6
Low Rate Initial Production
LAIRCM is an Research, Development, Test, and Evaluation (RDT&E) program and, as such, has no Low Rate Initial Production (LRIP) activities, as those are the purview of the individual platforms.
Foreign Military Sales
Country |  |  | Date of Sale |  | Quantity |  | Total Cost $M |  | Memo
Germany |  |  | 2011-06-20 |  | 6 |  | 113.8 |  | Will modify two Head of State (HoS) Airbus A319CJ and four Bombardier Global 5000 aircraft.
Germany |  |  | 2009-04-24 |  | 2 |  | 82.8 |  | Will modify two HoS Airbus A340 aircraft.
Saudi Arabia |  |  | 2007-03-08 |  | 1 |  | 56.3 |  | Modification ongoing of one HoS Boeing 747 aircraft.
Bahrain |  |  | 2004-05-18 |  | 1 |  | 43.3 |  | Modified one HoS Boeing 747 aircraft, Interim Contractor Support ongoing.

## Table 13
Nuclear Cost
There are no Nuclear Cost data to display.

## Table 14
Unit Cost
Unit Cost Report
|  | BY2008 $M | BY2008 $M
Unit Cost |  | Current UCR Baseline (AUG 2009 APB) | Current Estimate (SEP 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 457 |  |  | 436.6
Quantity | 8 |  |  | 8
Unit Cost | 57.125 |  |  | 54.575 |  | -4.46
Average Procurement Unit Cost (APUC)
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
|  | BY2008 $M | BY2008 $M
Unit Cost |  | Original UCR Baseline (AUG 2009 APB) | Current Estimate (SEP 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 457 |  |  | 436.6
Quantity | 8 |  |  | 8
Unit Cost | 57.125 |  |  | 54.575 |  | -4.46
Average Procurement Unit Cost (APUC)
Cost | 0 |  |  | 0
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --

## Table 15
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[8 empty] | BY2008 $M |  |  |  |  | TY $M
|  |  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  |  | AUG 2009 |  |  |  | 57.125 |  | N/A |  |  | 54.825 |  | N/A
APB as of January 2006 |  |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  |  | AUG 2009 |  |  |  | 57.125 |  | N/A |  |  | 54.825 |  | N/A
Prior Annual SAR |  |  |  | DEC 2010 |  |  |  | 54.588 |  | N/A |  |  | 51.65 |  | N/A
Current Estimate |  |  |  | SEP 2011 |  |  |  | 54.575 |  | N/A |  |  | 51.638 |  | N/A
Initial PAUC Prod Est | Changes | [12 empty] | PAUC Current Est
| Econ |  | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
45.750 -0.338 0.000 0.000 0.000 6.226 0.000 0.000 5.888 51.638
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [12 empty] | APUC Current Est
| Econ | Qty |  |  | Sch | Eng | Est |  | Oth |  | Spt | Total
0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 16
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | SEP 2001 | SEP 2001
Milestone C | N/A | N/A | AUG 2002 | AUG 2002
IOC | N/A | N/A | JUL 2004 | JUL 2004
Total Cost (TY $M) | N/A | N/A | 366 | 413.1
Total Quantity | N/A | N/A | 8 | 8
Prog. Acq. Unit Cost (PAUC) | N/A | N/A | 45.75 | 51.638

## Table 17
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 366.0 -- -- 366.0
Previous Changes
Economic |  | -2.7 |  | -- |  | -- |  | -2.7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 49.9 |  | -- |  | -- |  | 49.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 47.2 |  | -- |  | -- |  | 47.2
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.1 |  | -- |  | -- |  | -0.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -0.1 |  | -- |  | -- |  | -0.1
Total Changes |  | 47.1 |  | -- |  | -- |  | 47.1
CE - Cost Variance |  | 413.1 |  | -- |  | -- |  | 413.1
CE - Cost & Funding |  | 413.1 |  | -- |  | -- |  | 413.1

## Table 18
Summary Base Year 2008 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 383.6 -- -- 383.6
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 53.1 |  | -- |  | -- |  | 53.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 53.1 |  | -- |  | -- |  | 53.1
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.1 |  | -- |  | -- |  | -0.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -0.1 |  | -- |  | -- |  | -0.1
Total Changes |  | 53 |  | -- |  | -- |  | 53
CE - Cost Variance |  | 436.6 |  | -- |  | -- |  | 436.6
CE - Cost & Funding |  | 436.6 |  | -- |  | -- |  | 436.6
Previous Estimate: December 2010

## Table 19
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Decrease due to Congressional general rescissions in FY 2011. (Estimating) | -0.1 | -0.1
RDT&E Subtotal | -0.1 | -0.1
Change Explanations Memo
FY 2011 BA reflects changes from $17.2M budgeted to the $17.1M actual.

## Table 20
Contracts
General Contract Memo
Major Contracts for the LAIRCM RDT&E program are complete.
No contracts

## Table 21
Deliveries and Expenditures
The unit of measure is one aircraft modified with the LAIRCM system. The eight (8) development deliveries consist of (2) C-17s, (1) C-130H, (1) C-5, (1) C-130J, (1) AC-130H, (2) Air Force Special Operations Command
(AFSOC) C-130 variants. The remaining two aircraft to be modified are the AFSOC EC-130J and AC-130U.
Delivery and Expenditure data as of October 5, 2011.
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 6 |  | 6 |  | 8 | 75%
Production | 0 |  | 0 |  | 0 | --
Total Program Quantities Delivered | 6 |  | 6 |  | 8 | 75%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 413.1 | Years Appropriated |  |  | 10
Expenditures To Date | 372.6 | Percent Years Appropriated |  |  | 90.91%
Percent Expended | 90.2% | Appropriated to Date |  |  | 405.6
Total Funding Years | 11 | Percent Appropriated |  |  | 98.18%

## Table 22
Operating and Support Cost
Assumptions And Ground Rules
Major Defense Acquisition Program (MDAP) funding ends in FY 2012 for the Research, Development, Test and Evaluation effort of the LAIRCM program. Production funding is provided by the platforms and is not included in this SAR. Systems upgrades to maintain currency with threats, increase operational capability, and increase Reliability, Availability and Maintainability will continue beyond FY 2012.
There is no antecedent system for LAIRCM.
Costs BY2008 $K
Cost Element | LAIRCM | No Antecedent
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | -- | --
Sustaining Support | -- | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | -- | --
Total Unitized Cost (Base Year 2008 $) | -- | --
Total O&S Costs $M | LAIRCM | No Antecedent
Base Year | -- | --
Then Year | -- | --