## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-454
TWS
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 3
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 7
Track To Budget |  | 8
Cost and Funding |  | 9
Low Rate Initial Production |  | 16
Nuclear Cost |  | 16
Foreign Military Sales |  | 16
Unit Cost |  | 17
Cost Variance |  | 20
Contracts |  | 23
Deliveries and Expenditures |  | 26
Operating and Support Cost |  | 27

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
Thermal Weapon Sight, AN/PAS-13(V) (TWS)
DoD Component
Army
Responsible Office
Responsible Office
COL Stephanie Foster | Phone | 703-704-3324
Project Manager Soldier Sensors & Lasers | Fax | 703-704-0062
ATTN: SFAE-SDR-SSL | DSN Phone | 654-3324
10170 Beach Road, Building 325 Fort Belvoir, VA 22060-5800 | DSN Fax | 654-0062
stephanie.l.foster.mil@mail.mil | Date Assigned | October 8, 2009
References
SAR Baseline (Production Estimate)
Under Secretary of the Army Approved Acquisition Program Baseline (APB) dated January 19, 2012
Approved APB
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated January 19, 2012
Mission and Description
The AN/PAS-13(V) Thermal Weapon Sight (TWS) allows the Soldier to acquire and engage targets in all weather conditions. The TWS program supports the Army's objectives by increasing the individual Soldier's situational awareness, lethality, mobility and survivability during periods of significantly reduced visibility. TWS is used with a variety of individual and crew served weapons. The TWS supports the tactical level of war enabling the individual Soldier to see, understand, and act first. The TWS program provides the Soldier with advanced imaging technologies today. The TWS consists of an uncooled thermal imaging device. It significantly improves mounted and dismounted operational capability and supports weapon system performance, by increasing target acquisition range and enabling both day and night vision through smoke, fog, battlefield obscurants and in extremely low light levels. The TWS is produced in three configurations (light, medium, and heavy) to support the target acquisition range of the varied weapon systems. The TWS satisfies an immediate capability gap providing thermal imagery for the individual Soldier and is poised to capitalize on advances in technology, providing enhancements in all operating environments as well as size, weight and power improvements.

## Table 4
Executive Summary
This is the initial SAR submission for the Thermal Weapon Sight (TWS) program.
The Army awarded contracts for the advanced development of the TWS to Hughes Aircraft Company and Rockwell International in 1981. Advanced development units were subjected to Developmental and Operations Test I (DT/OT) in 1986. A Milestone I/II In-Process Review (IPR) held in December 1990 provided approval for TWS to enter the Engineering and Manufacturing Development (EMD) phase. The Army awarded a contract to Hughes Aircraft Company in December 1990 for development, ruggedization, and production readiness of thirty TWS units. Pre- Production Qualification Test (PPQT) and Limited User Test (LUT) occurred in 1994. A Special In-Process Review (SIPR) held in February 1995 provided approval for the limited production of TWS systems. The Army conducted Initial Production Test (IPT) and Initial Operational Test and Evaluation (IOTE) October 1996-March 1997 on the Limited Production Units. The final TWS Operational Requirements Document (ORD) was approved April 1998.
The Program Executive Office Intelligence, Electronic Warfare & Sensors (PEO IEW&S) approved the TWS Milestone III decision in June 1998. TWS was an Acquisition Category (ACAT) III program at that time.
A single five year full rate production contract was awarded to Raytheon Company in June 1998, and was referred to as the Thermal Omnibus contract. The First Unit Equipped (FUE) date was March 1999. Following the Thermal Omnibus contract, two firm fixed priced five year production contracts were awarded in March 2004 to BAE Systems and DRS Optronics for continued procurement of additional TWS systems. These contracts were referred to as TWS II. Due to increases in the Army Acquisition Objective (AAO) following program inception and corresponding increases in procurement funding, TWS was designated as an ACAT II program in May 2007. By the fourth program year of the TWS II contracts, the maximum quantity ceiling had been awarded, resulting in the need for award of new production contracts. Three firm fixed priced five year production contracts were awarded in June 2007 to BAE Systems, DRS Optronics, and Raytheon Company for procurement of additional TWS systems. These contracts are referred to as TWS II Bridge. Due to continued increases to the TWS AAO, TWS was designated as an ACAT IC program in March 2011 based on total procurement funding. At present, the total procurement requirement for TWS is 237,788 systems. This includes the AAO of 215,411 plus authorized replacement of 22,377 unsupportable Thermal Omnibus and Limited Procurement TWS systems.
The final execution year of the TWS II Bridge contracts is FY 2012. A Period of Performance extension request for the TWS II Bridge contracts is currently in process to allow for procurement of the final 5% of TWS quantities over the FY 2013-2015 timeframe under the existing contracts. The period of performance extension would avoid
the potential of having to qualify another TWS vendor if a new competition were to be required for the FY 2013-2015 requirements. Delivery orders for the Army's FY 2012 TWS requirements are expected to be awarded by May 2012 under the current TWS II Bridge contracts.
There are no software-related issues with this program.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 6
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
MS III | JUN 1998 | JUN 1998 | JUN 1998 | JUN 1998
Full Rate Production (FRP) Decision | JUN 1998 | JUN 1998 | JUN 1998 | JUN 1998
First Unit Equipped (FUE) | MAR 1999 | MAR 1999 | MAR 1999 | MAR 1999
Acronyms And Abbreviations
FRP - Full Rate Production FUE - First Unit Equipped MS - Milestone
Change Explanations
None

## Table 7
Performance
Requirements Source:
Operational Requirements Document (ORD) dated 14 April 1998.
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Target Acquisition (L/M/H) | 700/1500/28 00 meters | 700/1500/28 00 meters | 550/1100/22 00 meters | 839/1441/26 90 meters | 839/1441/26 90 meters
System Weight (L/M/H) | 3.00/4.50/5.5 0 lbs | 3.00/4.50/5.5 0 lbs | 3.25/5.00/6.0 0 lbs | 2.12/3.27/3.9 4 lbs | 2.12/3.27/3.9 4 lbs
Power Consumption (operational hours per 24 hour period with 1 non- rechargeable battery set change, L/M/H) | 14/14/14 hrs | 14/14/14 hrs | 7/7/7 hrs | 16.6/14.4/14. 4 hrs | 16.6/14.4/14. 4 hrs
Field of View LWTS | 15 degrees | 15 degrees | 14 degrees | 16.5 degrees | 16.5 degrees
Field of View MWTS | 6/18 degrees (narrow/wide) | 6/18 degrees (narrow/wide) | 6/18 degrees (narrow/wide) | 6/19 degrees (narrow/wide) | 6/19 degrees (narrow/wide)
Field of View HWTS | 3/9 degrees (narrow/wide) | 3/9 degrees (narrow/wide) | 3/9 degrees (narrow/wide) | 3/9 degrees (narrow/wide) | 3/9 degrees (narrow/wide)
Reliability (MTBOMF) | 500 hours | 500 hours | 250 hours | 856 hours | 856 hours
Acronyms And Abbreviations
hrs - hours
HWTS - Heavy Weapon Thermal Sight
L/M/H - Light/Medium/Heavy Weapon Thermal Sight lbs - pounds
LWTS - Light Weapon Thermal Sight
MTBOMF - Mean Time Between Operational Mission Failure MWTS - Medium Weapon Thermal Sight
ORD - Operational Requirements Document
Change Explanations
None
Memo
1/Battery consumption based on 20/60/20 hot/basic/cold composite per Operation Mode Summary. 2/Degrees narrow/wide derived from Operational Requirements Document width of view requirement. 3/Demonstrated Performance represents average of all TWS manufacturers.

## Table 8
Track To Budget
General Memo
The Procurement line for TWS is a shared line. Through FY 2014, all funds in this line are for TWS. During the period FY 2015-2017, the procurement funds are shared between TWS and the Family of Weapon Sights (FWS) program. Beyond FY 2017, all funds in this line will be used for FWS.
The RDT&E line is also a shared line which supports various other Project Manager Soldier, Sensors and Lasers (PM SSL) development activities.
RDT&E
APPN 2040 BA 05 PE 0604710A (Army)
Project L67 Soldier Night Vision Devices (Shared)
This budget line is shared with Project Manager Soldier Sensors & Lasers
Procurement
APPN 2035 BA 02 PE 0311100A (Army)
ICN K22900 Communications & Electronic Systems
(Shared)
Budget line shared with Project Manager Soldier Sensors & Lasers and Communications & Electronic Systems
K22900 is the Standard Study Number for Procurement funding.

## Table 9
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY1998 $M |  |  | BY1998 $M | TY $M
Appropriation | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 72.1 | 72.2 | 79.4 | 72.1 | 72.6 | 72.6 | 72.6
Procurement | 2395.5 | 2395.5 | 2638.2 | 2383.9 | 2883.5 | 2883.5 | 2881.1
Flyaway | 2240.9 | -- | -- | 2217.5 | 2696.4 | -- | 2677.9
Recurring | 2236.3 | -- | -- | 2212.9 | 2691.3 | -- | 2672.8
Non Recurring | 4.6 | -- | -- | 4.6 | 5.1 | -- | 5.1
Support | 154.6 | -- | -- | 166.4 | 187.1 | -- | 203.2
Other Support | 12.8 | -- | -- | 12.8 | 13.9 | -- | 13.9
Initial Spares | 141.8 | -- | -- | 153.6 | 173.2 | -- | 189.3
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 2467.6 | 2467.7 | N/A | 2456 | 2956.1 | 2956.1 | 2953.7
Confidence Level for Current APB Cost 50% - In accordance with Army policy and guidance from the Office of the Deputy Assistant Secretary of the Army for Cost and Economics, the confidence level of the Thermal Weapon Sight Acquisition Program Baseline (APB) cost estimate (approved on January 19, 2012) is 50%. It is difficult to calculate mathematically the precise confidence levels associated with life cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Notes:
(1) Baseline approved January 2012 in BY98 $M.
(2) TWS Program Acquisition Unit Cost (PAUC) and Average Procurement Unit Cost (APUC) values represent notional generic TWS system. PAUC & APUC values for Light, Medium, & Heavy variants allocate Non-Production Other Procurement Army and Research & Development funding on a quantity percentage basis.

## Table 10
Quantity | SAR Baseline Prod Est | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 237788 | 237788 | 237788
Total | 237788 | 237788 | 237788
Currently, the total procurement requirement for TWS is 237,788 systems, which includes the Army Acquisition Objective of 215,411 plus authorized replacement of 22,377 unsupportable Thermal Omnibus and Limited Production systems (per December 2010 Acquisition Decision Memorandum).
TWS Quantities Required per variant: TWS Light 64,904
TWS Medium 89,998
TWS Heavy 82,886

## Table 11
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
Appropriation |  | Prior | FY2012 |  | F |  | Y2013 | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  | To Complete |  | Total
RDT&E |  | 71.2 | 0 |  |  |  | 0 | 1.4 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 72.6
Procurement |  | 2479 | 186.9 |  |  |  | 82.2 | 79.7 |  | 46.2 |  | 4.2 |  |  | 2.9 |  | 0 |  | 2881.1
MILCON |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
PB 2013 Total |  | 2550.2 | 186.9 |  |  |  | 82.2 | 81.1 |  | 46.2 |  | 4.2 |  |  | 2.9 |  | 0 |  | 2953.7
|  | -- | -- |  |  |  | -- | -- |  | -- |  | -- |  |  | -- |  | -- |  | --
Quantity | Undistributed |  |  | Prior |  | FY2012 |  | FY2013 | FY2014 |  | FY | 2015 | FY | 2016 |  | FY2017 |  | To Complete |  | Total
Development | 0 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 0
Production | 0 210023 |  |  |  |  | 14990 |  | 4244 |  | 5551 |  | 2980 | 0 |  |  | 0 |  | 0 237788
PB 2013 Total | 0 210023 |  |  |  |  | 14990 |  | 4244 |  | 5551 |  | 2980 | 0 |  |  | 0 |  | 0 237788
| -- -- |  |  |  |  | -- |  | -- |  | -- |  | -- | -- |  |  | -- |  | -- --

## Table 12
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1991 | -- | -- | -- | -- | -- | -- | 9.5
1992 | -- | -- | -- | -- | -- | -- | 18.9
1993 | -- | -- | -- | -- | -- | -- | 8.4
1994 | -- | -- | -- | -- | -- | -- | 3.5
1995 | -- | -- | -- | -- | -- | -- | 1
1996 | -- | -- | -- | -- | -- | -- | 0.5
1997 | -- | -- | -- | -- | -- | -- | 0.5
1998 | -- | -- | -- | -- | -- | -- | 0.1
1999 | -- | -- | -- | -- | -- | -- | 0.2
2000 | -- | -- | -- | -- | -- | -- | 0.3
2001 | -- | -- | -- | -- | -- | -- | 3
2002 | -- | -- | -- | -- | -- | -- | 2.6
2003 | -- | -- | -- | -- | -- | -- | 1.2
2004 | -- | -- | -- | -- | -- | -- | 0.9
2005 | -- | -- | -- | -- | -- | -- | 0.4
2006 | -- | -- | -- | -- | -- | -- | 5.2
2007 | -- | -- | -- | -- | -- | -- | 5.7
2008 | -- | -- | -- | -- | -- | -- | 3.8
2009 | -- | -- | -- | -- | -- | -- | 4.3
2010 | -- | -- | -- | -- | -- | -- | 1.2
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | --
2013 | -- | -- | -- | -- | -- | -- | --
2014 | -- | -- | -- | -- | -- | -- | 1.4
Subtotal | -- | -- | -- | -- | -- | -- | 72.6

## Table 13
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1998 $M | Non End Item Recurring Flyaway BY 1998 $M | Non Recurring Flyaway BY 1998 $M | Total Flyaway BY 1998 $M | Total Support BY 1998 $M | Total Program BY 1998 $M
1991 | -- | -- | -- | -- | -- | -- | 10.6
1992 | -- | -- | -- | -- | -- | -- | 20.7
1993 | -- | -- | -- | -- | -- | -- | 9
1994 | -- | -- | -- | -- | -- | -- | 3.7
1995 | -- | -- | -- | -- | -- | -- | 1
1996 | -- | -- | -- | -- | -- | -- | 0.5
1997 | -- | -- | -- | -- | -- | -- | 0.5
1998 | -- | -- | -- | -- | -- | -- | 0.1
1999 | -- | -- | -- | -- | -- | -- | 0.2
2000 | -- | -- | -- | -- | -- | -- | 0.3
2001 | -- | -- | -- | -- | -- | -- | 2.9
2002 | -- | -- | -- | -- | -- | -- | 2.5
2003 | -- | -- | -- | -- | -- | -- | 1.1
2004 | -- | -- | -- | -- | -- | -- | 0.8
2005 | -- | -- | -- | -- | -- | -- | 0.4
2006 | -- | -- | -- | -- | -- | -- | 4.4
2007 | -- | -- | -- | -- | -- | -- | 4.8
2008 | -- | -- | -- | -- | -- | -- | 3.1
2009 | -- | -- | -- | -- | -- | -- | 3.5
2010 | -- | -- | -- | -- | -- | -- | 1
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | --
2013 | -- | -- | -- | -- | -- | -- | --
2014 | -- | -- | -- | -- | -- | -- | 1
Subtotal | -- | -- | -- | -- | -- | -- | 72.1

## Table 14
Annual Funding TY$
2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | 468 | 22.8 | -- | -- | 22.8 | -- | 22.8
1996 | 696 | 23.1 | -- | -- | 23.1 | -- | 23.1
1997 | 1600 | 45 | -- | -- | 45 | -- | 45
1998 | 1820 | 33.6 | 2.6 | -- | 36.2 | 3.6 | 39.8
1999 | 1019 | 29.7 | 2.6 | -- | 32.3 | 4.6 | 36.9
2000 | 1299 | 25.9 | 7.2 | -- | 33.1 | 6.9 | 40
2001 | 1288 | 25.9 | 5.8 | 1 | 32.7 | 3.3 | 36
2002 | 2132 | 28.4 | 2.8 | -- | 31.2 | 3.7 | 34.9
2003 | 3808 | 63.7 | 6.4 | -- | 70.1 | 3.7 | 73.8
2004 | 8247 | 161.1 | 4.9 | 4.1 | 170.1 | 7.3 | 177.4
2005 | 7526 | 65.4 | 2.4 | -- | 67.8 | 5.7 | 73.5
2006 | 19107 | 166.5 | 7.1 | -- | 173.6 | 7.1 | 180.7
2007 | 31652 | 284.5 | 24.6 | -- | 309.1 | 2.9 | 312
2008 | 37307 | 331.7 | 18 | -- | 349.7 | 30.2 | 379.9
2009 | 40172 | 341.9 | 59.7 | -- | 401.6 | 35.5 | 437.1
2010 | 30643 | 265 | 33.7 | -- | 298.7 | 21.3 | 320
2011 | 21239 | 187.2 | 22.1 | -- | 209.3 | 36.8 | 246.1
2012 | 14990 | 156.9 | 14.3 | -- | 171.2 | 15.7 | 186.9
2013 | 4244 | 48.5 | 28.8 | -- | 77.3 | 4.9 | 82.2
2014 | 5551 | 64.6 | 8.6 | -- | 73.2 | 6.5 | 79.7
2015 | 2980 | 35.2 | 7.5 | -- | 42.7 | 3.5 | 46.2
2016 | -- | -- | 4.2 | -- | 4.2 | -- | 4.2
2017 | -- | -- | 2.9 | -- | 2.9 | -- | 2.9
Subtotal | 237788 | 2406.6 | 266.2 | 5.1 | 2677.9 | 203.2 | 2881.1

## Table 15
Annual Funding BY$
2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1998 $M | Non End Item Recurring Flyaway BY 1998 $M | Non Recurring Flyaway BY 1998 $M | Total Flyaway BY 1998 $M | Total Support BY 1998 $M | Total Program BY 1998 $M
1995 | 468 | 23.1 | -- | -- | 23.1 | -- | 23.1
1996 | 696 | 23.2 | -- | -- | 23.2 | -- | 23.2
1997 | 1600 | 44.6 | -- | -- | 44.6 | -- | 44.6
1998 | 1820 | 33 | 2.5 | -- | 35.5 | 3.6 | 39.1
1999 | 1019 | 28.8 | 2.5 | -- | 31.3 | 4.5 | 35.8
2000 | 1299 | 24.9 | 6.9 | -- | 31.8 | 6.6 | 38.4
2001 | 1288 | 24.6 | 5.5 | 0.9 | 31 | 3.1 | 34.1
2002 | 2132 | 26.6 | 2.6 | -- | 29.2 | 3.5 | 32.7
2003 | 3808 | 58.6 | 5.9 | -- | 64.5 | 3.4 | 67.9
2004 | 8247 | 144.7 | 4.5 | 3.7 | 152.9 | 6.5 | 159.4
2005 | 7526 | 57.1 | 2.1 | -- | 59.2 | 5 | 64.2
2006 | 19107 | 141.7 | 5.9 | -- | 147.6 | 6.1 | 153.7
2007 | 31652 | 236.4 | 20.4 | -- | 256.8 | 2.4 | 259.2
2008 | 37307 | 271 | 14.7 | -- | 285.7 | 24.7 | 310.4
2009 | 40172 | 275.7 | 48.1 | -- | 323.8 | 28.6 | 352.4
2010 | 30643 | 209.7 | 26.6 | -- | 236.3 | 16.9 | 253.2
2011 | 21239 | 145.4 | 17.2 | -- | 162.6 | 28.5 | 191.1
2012 | 14990 | 119.8 | 10.9 | -- | 130.7 | 12 | 142.7
2013 | 4244 | 36.3 | 21.6 | -- | 57.9 | 3.7 | 61.6
2014 | 5551 | 47.6 | 6.3 | -- | 53.9 | 4.8 | 58.7
2015 | 2980 | 25.5 | 5.4 | -- | 30.9 | 2.5 | 33.4
2016 | -- | -- | 3 | -- | 3 | -- | 3
2017 | -- | -- | 2 | -- | 2 | -- | 2
Subtotal | 237788 | 1998.3 | 214.6 | 4.6 | 2217.5 | 166.4 | 2383.9

## Table 16
Low Rate Initial Production
| Initial LRIP Decision |  |  |  | Current Total LRIP
Approval Date | 2/15/1995 2/15/1997 2000 2764 ADM ADM 1995 1997 1997 1998
Approved Quantity
Reference
Start Year
End Year
A Special In Process Review held February 1995 type classified TWS Limited Procurement Urgent and provided approval for the limited production of up to 2000 systems. The Army awarded a total of 1164 systems to Hughes Aircraft beginning in April 1995. The Army conducted Initial Production Test and Initial Operational Test and Evaluation October 1996-March 1997. Based on favorable results from these tests and a Statement of Urgent Need for TWS from the US Army Infantry Center, the Army increased the limited production quantity threshold to 3000 units. The Army awarded an additional 1600 systems to Hughes Aircraft in April 1997, bringing the total number of limited production systems awarded to 2764.
Foreign Military Sales
Country |  | Date of Sale | Quantity | Total Cost $M |  | Memo
Thailand |  | 2002-08-20 | 33 | 0.6 |  | 33 Thermal Weapon Sights (Medium variant) to Thailand. Unit Cost $19,316. Contract DAAB07-98-C-J815. MOD P00080.
Czech Republic |  | 2002-08-02 | 2 | 0 |  | 2 Thermal Weapon Sights (Heavy variant) to Czech Republic. Unit Cost $21,197. Contract DAAB07-98-C-J815. MOD P00080.
Thailand |  | 2002-08-02 | 4 | 0.1 |  | 2 Thermal Weapon Sights (Heavy variant) to Thailand. Unit Cost $21,197. Contract DAAB07-98-C-J815. MOD P00080.
Nuclear Cost
None

## Table 17
Unit Cost
Unit Cost Report
|  | BY1998 $M | BY1998 $M
Unit Cost |  | Current UCR Baseline (JAN 2012 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2467.7 |  |  | 2456
Quantity | 237788 |  |  | 237788
Unit Cost | 0.01 |  |  | 0.01 |  | 0
Average Procurement Unit Cost (APUC)
Cost | 2395.5 |  |  | 2383.9
Quantity | 237788 |  |  | 237788
Unit Cost | 0.01 |  |  | 0.01 |  | 0
|  | BY1998 $M | BY1998 $M
Unit Cost |  | Original UCR Baseline (JAN 2012 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2467.7 |  |  | 2456
Quantity | 237788 |  |  | 237788
Unit Cost | 0.01 |  |  | 0.01 |  | 0
Average Procurement Unit Cost (APUC)
Cost | 2395.5 |  |  | 2383.9
Quantity | 237788 |  |  | 237788
Unit Cost | 0.01 |  |  | 0.01 |  | 0

## Table 18
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[7 empty] | BY1998 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | JAN 2012 |  |  |  | 0.01 |  | 0.01 |  |  | 0.012 |  | 0.012
APB as of January 2006 |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | JAN 2012 |  |  |  | 0.01 |  | 0.01 |  |  | 0.012 |  | 0.012
Prior Annual SAR |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current Estimate |  |  | DEC 2011 |  |  |  | 0.01 |  | 0.01 |  |  | 0.012 |  | 0.012
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
0.012 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.012
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [11 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
0.012 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.012

## Table 19
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone III | N/A | N/A | JUN 1998 | JUN 1998
FUE | N/A | N/A | MAR 1999 | MAR 1999
Total Cost (TY $M) | N/A | N/A | 2956.1 | 2953.7
Total Quantity | N/A | N/A | 237788 | 237788
Prog. Acq. Unit Cost (PAUC) | N/A | N/A | 0.012 | 0.012

## Table 20
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 72.6 | 2883.5 | -- | 2956.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | -- | 12.6 | -- | 12.6
Quantity | -- | -- | -- | --
Schedule | -- | -0.1 | -- | -0.1
Engineering | -- | -- | -- | --
Estimating | -- | -30 | -- | -30
Other | -- | -- | -- | --
Support | -- | 15.1 | -- | 15.1
Subtotal | -- | -2.4 | -- | -2.4
Total Changes | -- | -2.4 | -- | -2.4
CE - Cost Variance | 72.6 | 2881.1 | -- | 2953.7
CE - Cost & Funding | 72.6 | 2881.1 | -- | 2953.7

## Table 21
Summary Base Year 1998 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes | 72.1 | 2395.5 | -- | 2467.6
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -23.4 | -- | -23.4
Other | -- | -- | -- | --
Support | -- | 11.8 | -- | 11.8
Subtotal | -- | -11.6 | -- | -11.6
Total Changes | -- | -11.6 | -- | -11.6
CE - Cost Variance | 72.1 | 2383.9 | -- | 2456
CE - Cost & Funding | 72.1 | 2383.9 | -- | 2456
Previous Estimate:

## Table 22
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 12.6
Acceleration of procurement buy profile. Funding increase in FY 2013 President's Budget enabled Thermal Weapon Sight program office to accelerate system buy. | 0 | -0.1
(Schedule)
Estimating variance due to decreased hardware cost, decreased ancillary overhead and adjusted funding profile per President's Budget FY 2013. No impact to program execution. (Estimating)
-16.6 -21.3
Adjustment for current and prior escalation. (Estimating) -6.8 -8.7
Adjustment for current and prior escalation. (Support) -0.6 -0.6 Increase in Initial Spares since the January 2012 Acquisition Program Baseline.
Current estimate reports actuals for FY 2011 and includes Initial Spares for Helmet Mounted Devices (HMD). (Support)
+12.4 +15.7
Procurement Subtotal -11.6 -2.4

## Table 23
Contracts
General Contract Memo
This is the first time this program is being reported, therefore this is the first time each of the current three TWS contracts is being reported.
Appropriation: Procurement
Contract Name Thermal Weapon Sight II Bridge
Contractor Raytheon Company
Contractor Location 2501 W University Drive M/S 8064 PO Box 801 M/S 8064
McKinney, TX 75070-0801
Contract Number, Type W91CRB-07-D-0029, FFP
Award Date June 26, 2007
Definitization Date July 01, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
63.4 N/A 5049 361.9 N/A 39400 419.4 419.4
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to increases in quantity. The total quantity of TWS systems procured on the 0029 contract as of January 31, 2012 is:
Direct Army 39,400
Raytheon's Thermal Weapon Sight II Bridge contract is a five year firm fixed price Indefinite Delivery Indefinite Quantity contract for procurement of Light, Medium, and Heavy Weapon Thermal Sights, associated spare parts, special tools, and test equipment. Annual delivery orders are competed among the three Thermal Weapon Sight II Bridge contractors (BAE, DRS, and Raytheon), with each acceptable offeror receiving a minimum quantity order, and the balance of each year's requirements awarded to the offeror deemed to be the best value to the Government.

## Table 24
Appropriation: Procurement
Contract Name Thermal Weapon Sight II Bridge
Contractor BAE Systems Information and Electronic Systems Integration Inc
Contractor Location 2 Forbes Road
Lexington, MA 02421-7306 Contract Number, Type W91CRB-07-D-0030, FFP Award Date June 26, 2007
Definitization Date July 01, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
183.2 N/A 9322 774.4 N/A 72711 832.0 832.0
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to increases in quantity. Total TWS system quantity procured under contract 0030 thru January 31, 2012 is:
Direct Army 72,711
Army Long Range Sniper Night Sight 1930 USMC/Navy 5330
Air Force 33
Other 364
BAE's Thermal Weapon Sight II Bridge contract is a five year firm fixed price Indefinite Delivery Indefinite Quantity contract for procurement of Light, Medium, and Heavy Weapon Thermal Sights, associated spare parts, special tools, and test equipment. Annual delivery orders are competed among the three Thermal Weapon Sight II Bridge contractors (BAE, DRS, and Raytheon), with each acceptable offeror receiving a minimum quantity order, and the balance of each year's requirements awarded to the offeror deemed to be the best value to the Government.

## Table 25
Appropriation: Procurement
Contract Name Thermal Weapon Sight II Bridge
Contractor DRS Sensors and Targeting Systems Ic
Contractor Location 2330 Commerce Park Drive NE Suite 2
Palm Bay, FL 32905-7721
Contract Number, Type W91CRB-07-D-0031, FFP
Award Date June 26, 2007
Definitization Date July 01, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
14.4 N/A 1000 480.3 N/A 32747 537.8 537.8
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to increases in quantities. Total TWS system quantity procured on the 0031 contract as of January 31, 2012 is:
Direct Army 32,747
Air Force 1407
USMC 6991
DRS' Thermal Weapon Sight II Bridge contract is a five year firm fixed price Indefinite Delivery Indefinite Quantity contract for procurement of Light, Medium, and Heavy Weapon Thermal Sights, associated spare parts, special tools, and test equipment. Annual delivery orders are competed among the three Thermal Weapon Sight II Bridge contractors (BAE, DRS, and Raytheon), with each acceptable offeror receiving a minimum quantity order, and the balance of each year's requirements awarded to the offeror deemed to be the best value to the Government.

## Table 26
Deliveries and Expenditures
Deliveries To Date | Plan To | Date | Actual To Date | Total Quantity | Percent Delivered
Development | 0 |  | 0 | 0 | --
Production | 199404 |  | 195864 | 237788 | 82.37%
Total Program Quantities Delivered | 199404 |  | 195864 | 237788 | 82.37%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 2953.7 | Years Appropriated |  |  | 22
Expenditures To Date | 2550.3 | Percent Years Appropriated |  |  | 81.48%
Percent Expended | 86.34% | Appropriated to Date |  |  | 2737.1
Total Funding Years | 27 | Percent Appropriated |  |  | 92.67%
Data is through December 31, 2011.

## Table 27
Operating and Support Cost
Assumptions And Ground Rules
The Thermal Weapon Sight (TWS) Operating and Support (O&S) costs assume a Peacetime Operating Tempo of 84 hours per annum (84 hours per Operational Mode Summary/Mission Profile [OMS/MP]). O&S costs assume an average system life of 20 years, and reflect an average annual sustainment cost of BY1998 $K 0.084 for each of the three Thermal Weapon Sight variants (Light, Medium & Heavy). O&S costs are based on the Program Office Estimate (POE) dated October 31, 2011, and validated by Suffciency Review conducted by the Office of Deputy Assistant Secretary Army - Cost & Economics.
TWS O&S Maintenance includes Contractor Logistics Support (CLS) provided by Regional Support Centers (RSCs).
TWS O&S Sustaining Support includes Sustainment Support & Technical Services.
TWS O&S Other includes Second Destination Transportation, Replacement Batteries, Chargers, Testers and Brackets, as well as Disposal Costs at the end of system life.
Costs BY1998 $K
Cost Element | TWS Thermal Weapon Sight | AN/PVS-4 & AN/TVS-5 Sights
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | 0.066 | --
Sustaining Support | 0.001 | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | 0.017 | --
Total Unitized Cost (Base Year 1998 $) | 0.084 | --
Total O&S Costs $M | TWS | AN/PVS-4 & AN/TVS-5 Sights
Base Year | 398.3 | --
Then Year | 580.4 | --
Operating & Support costs for the antecedent systems - AN/PVS-4 & AN/TVS-5 Sights - are not currently available. Per Operational Requirements Document (ORD) for the Thermal Weapons Sight (TWS) dated April 14, 1998, the TWS family will replace AN/PVS-4 & AN/TVS-5 Sights. Communications & Electronics Command (CECOM) has directed units to discontinue expending funds on maintenance of AN/PVS-4 & AN/TVS-5 Sights. TWS is the authorized substitute for the AN/PVS-4 & AN/TVS-5 Sights. TWS systems should be requisitioned in lieu of repairing the antecedent systems.
Disposal costs are estimated to total $187K BY 1998 / $324K TY and are included in the O&S costs shown above.